## Slide 1: Adaptive Management in Refugee Programming: Lessons from Re:BUiLD Webinar, September 6, 2023

## Slide 2
The Re:BUiLD program
Re:BUiLD’s approach to adaptive management
What we have been learning
Recommendations

## Slide 3
The Re:BUiLD Program

## Slide 4
Why adaptive management?
Lack of evidence about what works
Complexity of the challenge to be solved
Uncertain and rapidly changing context
Re:BUiLD is a multi-faceted program to support urban refugees to build sustainable livelihoods in East Africa and inspire evidence-based systemic change globally
Goal: Refugees and vulnerable host communities in Nairobi and Kampala achieve economic self-reliance
Target: 20,000 refugees and host residents
Timeline: 5 years
Pillars:
Service Provision: Delivering livelihoods services to individuals and community-level interventions supporting local economies and social cohesion
Evidence & Learning: Gathering evidence and learning to demonstrate what works
Influence & Adoption: Encouraging adoption of program evidence and learning, to change policies, practices and investment globally
1
2
3

## Slide 5
Re:BUiLD’s approach to adaptive management

## Slide 6
Assumption: the solution to achieve the program goal is unknown.
Tactics: considered a wide-variety of intervention options using evidence review and broad consultation.
Selected from the options to form a hypothesis of what may work achieve the goal.
What’s different: High-level theory of change, treated as a hypothesis, as opposed to a roadmap, for impact.
Hypotheses around promising solutions
Assumption: regular information is needed to test our hypotheses.
Tactics: embedded various parallel evidence-generation and learning channels, tailored to each intervention.
What’s different: Learning-orientation throughout the entire program life-cycle as opposed to waiting until end-point, or at best mid-point, to test what’s working.
Channels for generating evidence and learning
Assumption: changes to program design and delivery are expected.
Tactics: designed detailed, and pro-active, frameworks to reflect on new information and make decisions to adapt. Included formal governance, decision matrix, and strategy testing.
What’s different: No expectation that the program design would remain the same for the full five years, but clear expectations for how decisions would be made.
At the outset, Re:BUiLD focused on three key strategies to design an adaptive program
Framework for governance and decision making
+
+
Notes: * Unless it’s a research program, humanitarian programs are frequently presented as “known”. The key shift here is in how the theory of change is viewed. It’s an informed hypothesis, not a roadmap to success.

## Slide 7
What we have been learning

## Slide 8
requires programs to plan differently
The design phase focused on planning the process for making program design decisions, as opposed to a detailed five-year program design. Notably, this enabled Re:BUiLD to respond flexibly during COVID.
can be limited by a focus on targets
Pressure (real or perceived) to achieve program targets was sometimes in conflict with the adaptive programming principles of learning and making changes based on new information.
de-risks creativity and innovation
The Re:BUiLD team felt confident incorporating some novel approaches into the program design because intentional testing was built-in, providing the opportunity to fail fast and pivot if needed.
benefits from tailored learning methodologies
Because Re:BUiLD does not adopt a one-size-fits-all approach to learning, the team is able to balance the need for timely information and rigorous evidence.
In the first two years of Re:BUiLD, we learned that adaptive management and adaptation…

## Slide 9
Donor policies
The IKEA Foundation policies not only permitted, but actively encouraged, adaptation.
Multiyear and flexible funding
Funding is for 5 years, with an additional 6 month planning grant, allowing the time required for trial and error.
Internal policies
Operational policies, such as finance and procurement, are often designed for linear programming.
Leadership support
Re:BUiLD program leadership actively models adaptive principles, values learning, and supports change when proposed.
Participatory and decentralized decision making
All Re:BUiLD team members have opportunities to share learnings and ideas for adaptation.
Access to and use of data
The availability of rich data has been a key enabler of learning. At the same time, synthesizing the volume of information has proven complex.
Enablers and constraints of adaptive programming that we experienced in Re:BUiLD include…

## Slide 10
Recommendations

## Slide 11
For Implementers
Socialize adaptive management approaches and expectations with both program and operations functions early on
Establish a predictable schedule of reflection and adaptation moments aligned with the operational planning cycle
Build in a flexible budget
Focus on defining frameworks to make decisions up front, as opposed to building out the detailed project design
Treat theories of change as an aid to guide thinking and to test hypotheses
Invest in data use and learning capacity
Incentivize learning
From our experience, we offer the following practical recommendations to best implement adaptive management approaches from day one… (1/2)

## Slide 12
Anticipate adaptation in grant structures
For Donors
Provide multiyear and flexible funding
Value learning outcomes
From our experience, we offer the following practical recommendations to best implement adaptive management approaches from day one… (2/2)

## Slide 13
Thank you
https://rebuild.rescue.org/